## Sheet
**Project Plan**
| Task Name | Duration | Dependencies | Status | Resources
| --- | --- | --- | --- | ---
| Create Project Charter | 1 day | None | Not Started | Leadership team
| Conduct Requirements Gathering | 2 weeks | Create Project Charter | Not Started | Product Manager, Stakeholders
| Develop High-Level Design | 2 weeks | Conduct Requirements Gathering | Not Started | Engineers, Designers
| Create Detailed Design | 4 weeks | Develop High-Level Design | Not Started | Engineers, Designers
| Develop Prototype | 4 weeks | Create Detailed Design | Not Started | Engineers, Designers
| Conduct User Acceptance Testing | 2 weeks | Develop Prototype | Not Started | QA team, Users
| Finalize Documentation | 1 week | Conduct User Acceptance Testing | Not Started | Technical Writer
| Deploy to Production | 1 week | Finalize Documentation | Not Started | Operations team
| Launch Product | 1 week | Deploy to Production | Not Started | Marketing team
| Monitor and Improve Product | Ongoing | Launch Product | Ongoing | Product Manager, Engineers